## Risk Register
Risk Register | [16 empty] | Date of Assessment / Review : | 2013-01-22 11:42 |  |  |  | Lookup References
1 | = Next Ref | [12 empty] | Calculated
Ref. | Risk Raiser | Date | Risk Name or Description | Causes | Consequences | Existing Controls | Control Evaluation | Risk Category | Consequence | Likelihood | Row | Col | RC | Risk Rating | Risk Score | Risk Accepted | Risk Owner | Risk Treatment Plan (refer no. & tab) | Updated | Risk Status | Next Review Date | Control Evaluation | Risk Area | Consequence | Likelihood | Risk Status
[11 empty] | #N/A | #N/A | #N/A | [8 empty] | Satisfactory | Compliance/ statutory | Insignificant | Rare | Under Treatment
[11 empty] | #N/A | #N/A | #N/A | [8 empty] | Reservations | Legal/ commercial | Minor | Unlikely | Under Review
[11 empty] | #N/A | #N/A | #N/A | [8 empty] | Unsatisfactory | Political/ economic | Moderate | Possible | Treated
[11 empty] | #N/A | #N/A | #N/A | [8 empty] | Not Set | Financial/ funding | Major | Likely
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Management | Critical | Almost Certain
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Operational
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Service delivery
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Health & Safety
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Human resources
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Stakeholders (clients/ suppliers)
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | IT/ information management
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Security
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
Note 1: The default risk rating column colour is green. This will change once the risk assessment has been made
Note 2: If more lines are required copy rows above the solid black line and insert. Do not enter additional risks below solid black line

## Instructions
How to use the risk register tool
1 | On line 1 of the "Risk Register" worksheet enter the name of the risk assessment or risk review)
2 | Enter the date of the risk assessment or risk review in the field on the top right of the spreadsheet
3 | At the risk identification stage, enter the reference number of the risk into the "Ref" field
4 | Enter the name of the person identifying the risk into the "Risk Raiser" field (optional)
5 | Enter the date when the risk was raised or identified. (This could be at the initial stage of assessment or at the review stage)
6 | Enter the risk description clearly identifying the nature of the risk (Risk = the chance of something happening which will impact on objectives*)
7 | Describe the causes or contributing factors to the risk
8 | Describe the consequences if the risk occurs
9 | Detail the existing controls in place to manage the risk (not future actions or treatment strategies)
10 | Evaluate the effectiveness of the controls using the criteria in the "Risk Assessment Criteria" worksheet
11 | Click on the "Risk Categories" field for a list of options to assign the risk to an area. Select the most appropriate area (source) of the risk
12 | Click on the consequence field for a list of five options of consequence listed in the "Risk Assessment Criteria" worksheet. Select the assessed risk consequence (with controls in place)
13 | Click on the likelihood field for a list of five options of consequence listed in the "Risk Assessment Criteria" worksheet. Select the assessed risk likelihood (with controls in place)
14 | The "Risk Level" field will be automatically populated with the level of risk based on the plotting of the risk in the risk matrix in the "Risk Category and Risk Matrix" worksheet
15 | The "Risk Score" field will be automatically populated with the risk score based on the plotting of the risk in the risk matrix in the "Risk Area and Risk Matrix" worksheet. Note: the score ranges from 1 to 25
16 | Click on the "Risk Accepted Y/N" field for the options. Based on the risk level (refer to "Risk Decision Point" table in the "Risk Category and Risk Matrix" worksheet), select "Yes" or "No" from the list
17 | Enter the risk owner. Note: the risk owner must have the responsibility for taking action on, or mitigating the risk
18 | Where risk treatment (mitigation) plans are required, enter the risk treatment number from the "Risk Treatment" worksheet.
19 | To add blank risk treatment forms, right click on the "Risk Treatment" worksheet and copy. Then rename/renumber the risk treatment
20 | Enter the date that when the risk was reviewed (following the risk assessment)
21 | Click on the "Status" field for a list of options, "Under treatment", "Under review", or "Treated"
22 | Enter the next review date for the review of the risk
23 | When updating the risk register, copy the file and archive the old file. This allows the risk register to remain a live and active document
24 | To Rank the risks from highest to lowest, click on the top of Row P so that that whole column is highlighted. Click on the Data tab at the top of the sheet then click on the SORT button.
In the sort field select Column P and then sort on values. Select order "Z to A" so that the risks are sorted by the highest scores in the risk register.
25 | An example risk register is contained in the Tab, "Example Risk Register" which contains example risks. Try entering new risks or re-assessing example risks using this tab.
Risk Area and Risk Matrix Worksheet
1 | The "Risk Category" table is used to select the most appropriate source of risk
2 | The "Risk Matrix" diagram is used as a manual reference for assigning risk level and risk score. This is obtained by using the consequence and likelihood criteria in the "Risk Assessment Criteria" tab
3 | The risk levels are based on the assessment of the risk (Extreme High, High, Medium or Low)
Risk Assessment Criteria Worksheet
1 | Select the appropriate "Financial Consequence Criteria" (based on the context of the risk assessment - Organisation/ Project).
2 | Assess risks using the "Consequence" criteria table (incorporating the appropriate financial impact table)
3 | Assess risks using the "Likelihood" table
4 | Evaluate the effectiveness of the aggregate affect of the existing control or controls in place to manage the risk
Risk Profile Worksheet
1 | The risks will be plotted automatically onto the "Risk Profile" model. The risk profile plots the position of the risks in the matrix based on the risk assessment
Risk Treatment Worksheet
1 | Enter the details of the risk treatment strategies and actions into the "Risk Treatment Plan" in the "Risk Treatment" worksheet
2 | To create additional risk treatments, copy the "Risk Treatment" worksheet and rename/renumber
3 | If numerous risk treatment plans are required, an additional document may need to be created to house the treatment plans
Guide on describing a risk
1 | A risk is a threat to meeting objectives or an impediment to success. A clear description of the problem is required for accurate assessment
2 | A verb describing a condition or state that is undesirable is needed in the risk description
For example,…"inability to", "lack of", "insufficient", "reduced ability to", "shortage of", etc.
3 | The causes or consequences are required to be documented to fully understand why the risk is occurring or can occur
4 | The consequences are required to be documented to understand the size and nature of the risk
* AS/NZS ISO 31000:2009 Risk management - Principles and guidelines

## Risk Area and Risk Matrix
Risk Areas/Categories
Risk Matrix
Compliance/ statutory |  |  |  | CONSEQUENCE
Legal/ commercial | LIKELIHOOD |  | VLOOKUP | Insignificant | Minor | Moderate | Major | Critical
Political/ economic |  | HLOOKUP |  | 1 | 2 | 3 | 4 | 5
Financial/ funding | LIKELIHOOD | Almost Certain | 1 | M(05) | H(10) | H(15) | E(20) | E(25)
Management |  | Likely | 2 | M(04) | M(08) | H(12) | H(16) | E(20)
Operational |  | Possible | 3 | L(03) | M(06) | H((09) | H(12) | H(15)
Service delivery |  | Unlikely | 4 | L(02) | L(04) | M(06) | M(08) | H(10)
Health & Safety |  | Rare | 5 | L(01) | L(02) | M(03) | M(04) | H(05)
Human resources |  |  |  | CONSEQUENCE
Stakeholders (clients/ suppliers) |  | Note: Risks are scored by the application of consequence and likelihood
IT/ information management
Security |  | Four risk levels are used in the development of the risk register
Risk Levels
|  | E | Extreme
|  | H | High
|  | M | Medium
|  | L | Low
Risk Decision Point
|  | Risk Rank | Qualified Acceptance with Adequate Controls
|  | Low | Yes
|  | Medium | Yes
|  | High | No
|  | Extreme | No

## Risk Assessment Criteria
Consequence Criteria Business
Level | Descriptor | Financial | Management Effort | Health & Safety | Health & Safety | Reputation/ community | Legal/ Compliance
1 | Insignificant | Loss, error or omission up to 1% of annual budget or projected revenue | An event, the impact of which can be absorbed through business as usual activity | An event, the impact of which can be absorbed through business as usual activity | First aid treatment required | Minor adverse local public or media attention or complaints | Minor compliance issues
2 | Minor | Loss, error or omission 1% - 5% of annual budget or projected revenue | An event, the consequences of which can be absorbed but management effort is required to minimise the impact, potential reallocation of resources | An event, the consequences of which can be absorbed but management effort is required to minimise the impact, potential reallocation of resources | Significant but reversible disability requiring hospitalisation | Attention from media and/or heightened concern by local community | Minor legal issues, non-compliances and breaches or regulations
3 | Moderate | Loss, error or omission 5% - 10% of annual budget or projected revenue | An event that can be managed under normal circumstances, additional resources required, potential reallocation of resources. | An event that can be managed under normal circumstances, additional resources required, potential reallocation of resources | Permanent disabling injury or disabling illness to one or more persons | Significant adverse media attention | Breach of regulation with investigation or report to authority with prosecution and/or moderate fine possible
4 | Major | Loss, error or omission 10% - 15% of annual budget or projected revenue | An event, which with proper management can be endured, may involve some changes in management, additional resources required | An event, which with proper management can be endured, may involve some changes in management, additional resources required | Single fatality and/or severe irreversible disability (>30%) to one or more persons | Serious public or media outcry (state coverage) | Major breach of regulation, prosecution or major litigation
5 | Critical | Loss, error or omission >15% of annual budget or projected revenue | An event so severe in nature it could lead to a significant restructure of the organisation or its major parts or a change in the management structure | Series of fatalities or significant irreversible disability, or significant irreversible effects to >10 persons | Series of fatalities or significant irreversible disability, or significant irreversible effects to >10 persons | Serious public or media outcry (national coverage) | Significant prosecution and fines, very serious litigation
Likelihood Criteria
[5 empty] | Level | Likelihood | Description | Probability
[5 empty] | 1 | Rare | May only occur only in exceptional circumstances. This event is known to have occurred elsewhere – once every 5+ years | <5%
[5 empty] | 2 | Unlikely | Could occur at some time – once every 5 years | 5% - 30%
[5 empty] | 3 | Possible | Might occur at some time – once every 3 years | 30% - 60%
[5 empty] | 4 | Likely | Will probably occur - once during the year | 60% - 90%
[5 empty] | 5 | Almost Certain | Is expected to occur in most circumstances - frequently during the year | > 90% - 100%
Control Evaluation
|  |  | Level | Descriptor | Status Test
|  |  | S | Satisfactory | Comprehensive effective controls fully in place
|  |  | R | Reservations | Reservations on the effectiveness of the controls
|  |  | U | Unsatisfactory | Controls are either not in place or have no affect on managing risks
|  |  | NS | Not Set | Controls and status are unknown

## Risk Profile
Risk Profile
Likelihood | Almost Certain | 0 | 0 | 0 | 0 | 0
| Likely | 0 | 0 | 0 | 0 | 0
| Possible | 0 | 0 | 0 | 0 | 0
| Unlikely | 0 | 0 | 0 | 0 | 0
| Rare | 0 | 0 | 0 | 0 | 0
|  | Insignificant | Minor | Moderate | Major | Critial
Consequence
Extreme
|  | High | Risk Tolerance
Medium
Low
Note: Risk plots are the numbers of risks in the cells in the matrix

## Risk Treatment 1
Risk Treatment Plan
Risk Ref/ID's |  | Risk Name(s)/Description
Current Risk Assessment (with Controls)
Controls Rating |  | Level of Risk |  | Risk Score | Acceptance Decision | Y/N
Predicted (Target) Risk Assessment Post Treatment
Controls Rating |  | Level of Risk |  | Level of Risk | Acceptance Decision | Y/N
Treatment Plan Ref. No. | Objective of Risk Treatment Plan
1. Proposed Actions
2. Resources required
3. Responsibilities
4. Timing
5.Reporting and Monitoring Required
Risk Treatment Owner |  | Date | Authorised By |  | Target Date Completion
|  |  | Date Completed |  | Approved

## Example Risk Register
Risk Register | [16 empty] | Date of Assessment / Review : | 2013-01-22 11:42 |  |  |  | Lookup References
11 | = Next Ref | [12 empty] | Calculated
Ref. | Risk Raiser | Date | Risk Name or Description | Causes | Consequences | Existing Controls | Control Evaluation | Risk Category | Consequence | Likelihood | Row | Col | RC | Risk Rating | Risk Score | Risk Accepted | Risk Owner | Risk Treatment Plan (refer no. & tab) | Updated | Risk Status | Next Review Date | Control Evaluation | Risk Area | Consequence | Likelihood | Risk Status
5 | Group workshop | 2012-06-01 | Failure to adequately report to the regulator resulting in potential fines and penalties | Failure to follow procedures, use of incorrect procedures | Financial impact, potential reputation impact | Governance framework, Reporting, Policies & Procedures | Reservations | Legal/ commercial | Major | Possible | 3 | 4 | 34 | High | 12 | N | Chief Executive Officer | Treatment Plan #1 |  | Under Treatment | 2013-09-01 | Satisfactory | Compliance/ statutory | Insignificant | Rare | Under Treatment
2 | Group workshop | 2012-06-01 | Inability to raise adequate funding resulting in potential impact on program delivery | Insufficient focus, insufficient resource allocation | Impact on programs, potential reputation impact | Funding process, Grants, Financial controls | Reservations | Financial/ funding | Moderate | Possible | 3 | 3 | 33 | High | 9 | N | Chief Financial Officer | Treatment Plan #2 |  | Under Treatment | 2013-10-01 | Reservations | Legal/ commercial | Minor | Unlikely | Under Review
10 | Group workshop | 2012-06-01 | Inability to adequately (human) resource programes with possible program delays and reputation impact | Loss of staff, uncompetitive remuneration | Impact on programs, potential reputation impact | HR processes, Remuneration policy, Retention policy | Satisfactory | Human resources | Moderate | Unlikely | 4 | 3 | 43 | Medium | 6 | Y | Human Resources Manager | N/A |  | Treated | 2013-10-01 | Unsatisfactory | Political/ economic | Moderate | Possible | Treated
4 | Group workshop | 2012-06-01 | Failure of staff to follow procedures resulting in potential injury and health & safety incident | Inadequate training, failure to follow procedures | Loss time (off work) by staff, fines/ penalties | Health & Safety policy, health & safety procedures, training, internal health & safety reviews | Satisfactory | Health & Safety | Minor | Unlikely | 4 | 2 | 42 | Low | 4 | Y | Health & Safety Officer | N/A |  | Treated | 2013-10-01 | Not Set | Financial/ funding | Major | Likely
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Management | Critical | Almost Certain
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Operational
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Service delivery
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Health & Safety
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Human resources
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Stakeholders (clients/ suppliers)
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | IT/ information management
[11 empty] | #N/A | #N/A | #N/A | [9 empty] | Security
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A
Note 1: The default risk rating column colour is green. This will change once the risk assessment has been made
Note 2: If more lines are required copy rows above the solid black line and insert. Do not enter additional risks below solid black line

## Example Risk Treatment Plan
Risk Treatment Plan
Risk Ref/ID's |  | Risk Name(s)/Description
5 |  | Review and strengthen the reporting system and include in the audit process
Current Risk Assessment (with Controls)
Controls Rating | Reservations | Level of Risk | High | Risk Score | 12 | Acceptance Decision | N
Predicted (Target) Risk Assessment Post Treatment
Controls Rating |  | Level of Risk |  | Level of Risk |  | Acceptance Decision | Y/N | Note: Optional
Treatment Plan Ref. No. | Objective of Risk Treatment Plan
1 | To reduce the potential threat of fines and penalties arising from the risk of failure to adequately report in a timely manner
1. Proposed Actions | Review existing process, Review reporting mechanism, Develop draft change to process, Obtain CEO approval for revised process, Implement new reporting system
2. Resources required | Time (approximately 15 working days), No additional financial resources required - part of management time
3. Responsibilities | Financial Controller reporting to Chief Executive Officer
4. Timing | Three months
5.Reporting and Monitoring Required | Monitor progress on risk treatment plan monthly as part of the existing management process
Risk Treatment Owner |  | Date | Authorised By |  |  | Target Date Completion
Financial Controller |  | 2012-05-01 | Chief Executive Officer |  |  | Septemter 2012
|  |  | Date Completed |  |  | Approved